## Sheet1
PERT Diagram Key
Index | Name | Starting Week | Completion Week
A | Statement of Work | 1 | 1
B | Specification | 1 | 1
C | Database Setup | 1 | 1
D | Basic Upload Feature | 2 | 2
E | Publishing Uploads | 2 | 2
F | Views of Uploaded Papers | 2 | 2
G | Primitive Prototype | 2 | 2
H | Publication Test | 2 | 2
I | Draft Paper/Conference Paper | 3 | 4
J | Draft Purposal | 3 | 4
K | Paper Status | 3 | 3
L | Domain Checks | 3 | 3
M | Templates | 4 | 4
N | Feedback | 4 | 6
O | Revised Uploads | 4 | 6
P | Final Deliverable Tests and Features | 6 | 6
PERT Diagram
A
B
C
C
E
F
G
D
H
I
J
P
K
L
N
O
M